## Sheet1
Color Coding |  | Completed |  |  |  | SPRING 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[5 empty] | Date | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-27 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | All | 2022-01-25 | 2022-01-25 | 100%
| Confirm Project Team Roles | All | 2022-01-25 | 2022-01-25 | 100%
| Develop two business cases | All | 2022-01-25 | 2022-02-08 | 100%
| Develop Project Initiation Document (PID) | Lakshmi | 2022-02-08 | 2022-02-15 | 100%
| Produce initial Project Plan, RACI | Lakshmi | 2022-02-15 | 2022-02-22 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Shubham | 2022-02-22 | 2022-03-01 | 100%
| Produce Context Diagram, Define System Interfaces | Sathvik | 2022-02-22 | 2022-03-01 | 100%
| Define Business Requirements | Shubham | 2022-02-15 | 2022-03-22 | 100%
| Agree to System Requirements types | All | 2022-02-27 | 2022-03-22 | 100%
| Define Functional Decomposition | Sathvik | 2022-02-27 | 2022-03-22 | 100%
| Produce RCT document | Sathvik | 2022-02-27 | 2022-03-08 | 100%
| Decide which features to implement this semester | All | 2022-02-27 | 2022-03-01 | 100%
| Produce analysis diagrams (UML, DFD) | Sathvik | 2022-02-27 | 2022-03-01 | 100%
| Define functional requirements (User Stories) | Sathvik | 2022-02-27 | 2022-03-01 | 100%
| Update Project Plan with additional requirements tasks | Lakshmi | 2022-03-22 | 2022-03-29 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Nitesh | 2022-03-29 | 2022-04-12 | 100%
| Establish Github Project | Nitesh | 2022-03-29 | 2022-04-12 | 100%
| Database Design (ERD, Table spec) | Akshay | 2022-03-29 | 2022-04-05 | 100%
| Class Diagram (UML) | Akshay | 2022-04-05 | 2022-04-12 | 100%
| Sequence Diagram (UML) | Nitesh | 2022-04-05 | 2022-04-12 | 100%
| Populate test data in the database tables | Rohit | 2022-04-05 | 2022-04-12 | 100%
| Source code in GitHub repository, executable code ready for testing | Sagarika | 2022-04-05 | 2022-04-12 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | Sayali | 2022-04-05 | 2022-04-19 | 100%
| Coding & Implemenation | Nitesh | 2022-04-05 | 2022-04-19 | 100%
Feature Breakdown
03.01 Authenticate the user
| Validate login for Service Providers and Users | Sayali | 2022-04-12 | 2022-04-19 | 100%
03.02 Summarize the Account Details
| Profile page for Service Provider | Nitesh | 2022-04-12 | 2022-04-19 | 100%
| Service Provider : Add Descriptions, service hours, pictures and other informations. | Nitesh | 2022-04-12 | 2022-04-19 | 100%
| Service Provider : Edit fields on the page. | Nitesh | 2022-04-12 | 2022-04-19 | 100%
| Summary page for Users | Sayali | 2022-04-12 | 2022-04-19 | 100%
03.04 Register the Service Provider
| Registration page for Service provider | Nitesh | 2022-04-05 | 2022-04-12 | 100%
| Database connection | Akshay | 2022-04-05 | 2022-04-19 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Rohit | 2022-04-26 | 2022-05-10 | 100%
| Evaluate Features to be Tested | Rohit | 2022-04-26 | 2022-05-10 | 100%
| Design Test Cases | Sagarika | 2022-04-26 | 2022-05-03 | 100%
| Execute Test Cases | Sagarika | 2022-04-03 | 2022-05-10 | 100%
| Anaylze Test Results | Rohit | 2022-05-03 | 2022-05-10 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | All | 2022-05-03 | 2022-05-10 | 100%